## Instructions
RBQM Oversight Learning Resources
Developed collaboratively by the mindsON RBQM Expert Working Group (Dec 2025)
https://www.minds-on.org
The Expert Working Group (EWG) has developed four learning resources that are designed to assist the process of RBQM oversight per the diagram below. This approach is not designed to be applied in a prescriptive or burdensome manner. The learning resources should not be applied in a “box-checking” fashion but should be used to encourage critical thinking. The learning resources are intended to support thoughtful, risk-based application of RBQM.
Learning Resource A: RBQM Oversight Trial Assessment
The RBQM Oversight Level Matrix provides a structured, risk-based approach to help determine the required level of oversight for the trial. The results of this assessment serve as one of the key inputs into developing the RBQM oversight strategy – with the evaluation of five criteria—trial criticality, sponsor experience, service provider (e.g. CRO) history, process novelty, and geographical complexity. Each criterion has a description of situations that might be considered as a need for a low, medium or high level of RBQM oversight. Higher risk levels indicate greater need for oversight. This can then be used as an input into the development of an RBQM oversight strategy. The matrix is intended to guide critical thinking rather than serve as a strict scoring tool.
Learning Resource B: RBQM Competency Questions
The RBQM Competency Questions can be used to help assess the RBQM process itself against requirements from ICH E6(R3) and ICH E8(R1) as well as emerging best practice from industry based on Expert Working Group experience. It consists of nine questions along with model responses to those questions ranging from good, to better and best, intended to illustrate different levels of process maturity rather than prescribe a specific standard. It has various use cases such as during assessment of a service provider where the questions could be provided for written responses. If some, or all, aspects of RBQM are managed internally by an organization, it would not need to be used for each trial as the process is known. But it could be used to assess that internal process and the model answers could be used as a guide to developing that process further. It could also be used to assist during preparation and conduct of an audit. The results of this assessment complement the trial-level assessment described in Learning Resource A. The responses from this assessment should be used – together with the trial-level assessment from Learning Resource A - to inform development of the RBQM oversight strategy.
Learning Resource C: RBQM Oversight Example Mitigations
The RBQM Oversight Example Mitigations can be used to assist with developing a proportionate and fit-for-purpose RBQM oversight strategy. This resource aligns with the RBQM Oversight Trial Assessment so that any criteria that score medium or high can be translated into concrete actions across the common risk drivers of trial criticality, sponsor experience, service provider history, process novelty, and geographical complexity. By aligning mitigations with these criteria, sponsors can ensure their RBQM oversight remains proportionate, targeted, and evidence-based rather than generic or duplicative. The example mitigations in this resource are intended to prompt critical thinking rather than serve as a prescriptive checklist. These actions may be revisited during the trial as new information emerges or as risks evolve.
Learning Resource D: RBQM Reflective Questions
The RBQM Reflective Questions are intended to support ongoing evaluation of RBQM implementation during trial conduct . They are example questions grouped by category that are designed to assist in a conversation about the RBQM implementation. They can be used to gain an insight into the RBQM process in action and the discussions may lead to the RBQM oversight level being adjusted. These questions help surface evidence about how effectively risks – particularly those affecting participant safety or data reliability – are being managed. Unlike prescriptive checklists, these questions are intended to stimulate critical thinking, encourage dialogue across functions and between sponsor and service provider(s), and provide a practical way to verify that risk management activities are both meaningful and effective. The questions are grouped into nine areas and are provided below. They are intended to guide structured dialogue and support critical thinking, rather than serve as a formal scoring mechanism. Note that many of the questions relate to activities that should have occurred prior to First Participant First Visit.
Disclaimer:
The RBQM Oversight Learning Resources developed by the mindsON RBQM Expert Working Group (EWG) are intended for use by professionals with technical skills and knowledge in the pharmaceutical and biotechnology industries. Neither the EWG nor their respective employers make any warranties or assume any legal liability or responsibility for the accuracy, completeness, or usefulness of the information provided. It is the responsibility of the user to ensure that the information is suitable for their intended use. Neither the EWG nor their respective employers are responsible for any inaccuracies in the Learning Resources or for any advice provided. Additionally, the user is responsible for protecting their data from potential errors, viruses, or bugs, and is prohibited from distributing or selling the Learning Resources without written consent from the EWG. Neither the EWG nor their employers will be held liable for any damages resulting from the use of the Learning Resources. This document is provided 'as is' without warranty of any kind, either expressed or implied, including, but not limited to, the implied warranties of merchantability, fitness for a particular purpose or non-infringement.
This is not a validated Tool. Ensure validation as applicable per your company requirements.
The content can be modified or adopted to specific company needs.

## Resource B
Resource B: Questions to Help Assess RBQM Competency
Details of respondent:
| Question | Response | Follow up question | Accept Response Y/N
1 | Formal Risk Assessments How are trial-level and site-level risks differentiated and identified during planning?
2 | Stakeholder Engagement in Risk Assessments Are the right people involved in identifying and assessing risks (e.g. cross-functional input)?
3 | Critical to Quality Factors (CTQs) How are CTQs determined?
4 | QTLs/ARs Do the Quality Tolerance Limits / Acceptable Ranges directly stem from the top risks, and are they reviewed regularly?
5 | Risk Assessment Review Is there a process for risk assessment review after protocol changes or as the study progresses (living document vs. one-time exercise)?
6 | Mitigations Are risk mitigation actions tracked to completion?
7 | RBQM Outputs Do tools and reports (dashboards, KRI reports) lead to concrete actions/decisions in trial management? (Rather than just generating data with no follow-up.)
8 | RBQM Roles & Responsibilities How are RBQM roles and responsibilities agreed, reviewed and updated for a trial?
9 | Monitoring Strategy Is the monitoring approach (e.g., on-site vs. centralized focus) tailored based on study risks? How is the effectiveness of monitoring modifications evaluated and documented?

## Resource B Sample Answers
Resource B: Questions to Help Assess RBQM Competency
Sample answers
| Question | Response
1 | Formal Risk Assessments How are trial-level and site-level risks differentiated and identified during planning? | Good Risk Assessment is conducted prior to trial initiation with focus on risks with meaninful impact on CTQs with details of scoring risks to determine proportionality of management. Oversight evidence is documented and available for inspection readiness. Better As above plus including details of mitigation and contingency plans. Focused (suggested <20) key quality risks (excluding operational risks) being managed. Best As above plus study-specific KRIs and QTLs/ARs
2 | Stakeholder Engagement in Risk Assessments Are the right people involved in identifying and assessing risks (e.g., cross-functional input)? | Good Cross-functional participants are formally involved in the Risk Assessment Better As above plus a recognised approval process Best As above plus assignment of appropriate risk owners to lead oversight of risk review and communication.
3 | Critical to Quality Factors (CTQs) How are CTQs determined? | Acceptable CTQs may be provided by the sponsor to the CRO. If so, they are reviewed using knowledge from the CRO. Modifications may be suggested. If they are to be developed by the CRO, they are developed in collaboration with significant parties. CTQs are in alignment with Quality by Design principles per ICH E8 (R1) 3.3. Key risks on the study relate to one or more identified CTQs.
4 | QTLs/ARs Do the Quality Tolerance Limits / Acceptable Ranges directly stem from the top risks, and are they reviewed regularly? | Good Appropriate QTLs/ARs and their thresholds are determined by trial team SMEs and assigned to relevant CTQ risks. Where deviation beyond these ranges is detected, an evaluation is performed to determine if there is a possible systemic issue. There is an approach to try to detect the emergence of CTQ risks as issues as early as possible (e.g., using leading metrics and/or companion KRIs) Best As above plus thresholds are reviewed during the trial to check whether they are detecting emerging issues as expected.
5 | Risk Assessment Review Is there a process for risk assessment review after protocol changes or as the study progresses (living document vs. one-time exercise)? | Acceptable Risk Assessments are reviewed during the trial and the timing and/or triggers for those are clear. Timing includes milestones such as protocol amendment, significant quality issue and minimum frequency. Review may include removal/addition of risks, re-prioritizing and modification of risk controls as necessary. A broad range of stakeholders is included in the reviews.
6 | Mitigations Are risk mitigation actions tracked to completion? | Good Risk mitigation actions (additional controls that have been identified as part of the risk assessment) are clearly assigned and documented in relevant study plans, with owners and timelines, and tracked to completion Best As above plus mitigations are demonstrated to be effective.
7 | RBQM Outputs Do tools and reports (dashboards, KRI reports) lead to concrete actions/decisions in trial management? (Rather than just generating data with no follow-up.) | Good RBQM outputs are produced and available for review by the study team.RBQM outputs are reviewed in study team meetings and influence selected operational adjustments (e.g., monitoring frequency, site follow-up) Better As above plus actions are clearly assigned, with owners and timelines, and tracked to completion Best Actions from review of RBQM outputs are reviewed for effectiveness
8 | RBQM Roles & Responsibilities How are RBQM roles and responsibilities agreed, reviewed and updated for a trial? | Good All key roles at CRO and Sponsor are agreed between all parties up-front and documented (e.g., using a RACI). Responsibilities include all main RBQM and RBQM oversight activities. Best Regular review of the roles and responsibilities to ensure it is meeting the needs and requirements.
9 | Monitoring Strategy Is the monitoring approach (e.g., on-site vs. centralized focus) tailored based on study risks? How is the effectiveness of monitoring modifications evaluated and documented? | Good The planned level of on-site (including Source Data Verification) and centralized monitoring varies according to trial risk. Better As above plus it is modified during a trial on a site level based on continuous risk assessment Best As above plus how is the effectiveness of monitoring modifications evaluated and documented?”.