## Instructions
RBQM Oversight Learning Resources
Developed collaboratively by the mindsON RBQM Expert Working Group (Dec 2025)
https://www.minds-on.org
The Expert Working Group (EWG) has developed four learning resources that are designed to assist the process of RBQM oversight per the diagram below. This approach is not designed to be applied in a prescriptive or burdensome manner. The learning resources should not be applied in a “box-checking” fashion but should be used to encourage critical thinking. The learning resources are intended to support thoughtful, risk-based application of RBQM.
Learning Resource A: RBQM Oversight Trial Assessment
The RBQM Oversight Level Matrix provides a structured, risk-based approach to help determine the required level of oversight for the trial. The results of this assessment serve as one of the key inputs into developing the RBQM oversight strategy – with the evaluation of five criteria—trial criticality, sponsor experience, service provider (e.g. CRO) history, process novelty, and geographical complexity. Each criterion has a description of situations that might be considered as a need for a low, medium or high level of RBQM oversight. Higher risk levels indicate greater need for oversight. This can then be used as an input into the development of an RBQM oversight strategy. The matrix is intended to guide critical thinking rather than serve as a strict scoring tool.
Learning Resource B: RBQM Competency Questions
The RBQM Competency Questions can be used to help assess the RBQM process itself against requirements from ICH E6(R3) and ICH E8(R1) as well as emerging best practice from industry based on Expert Working Group experience. It consists of nine questions along with model responses to those questions ranging from good, to better and best, intended to illustrate different levels of process maturity rather than prescribe a specific standard. It has various use cases such as during assessment of a service provider where the questions could be provided for written responses. If some, or all, aspects of RBQM are managed internally by an organization, it would not need to be used for each trial as the process is known. But it could be used to assess that internal process and the model answers could be used as a guide to developing that process further. It could also be used to assist during preparation and conduct of an audit. The results of this assessment complement the trial-level assessment described in Learning Resource A. The responses from this assessment should be used – together with the trial-level assessment from Learning Resource A - to inform development of the RBQM oversight strategy.
Learning Resource C: RBQM Oversight Example Mitigations
The RBQM Oversight Example Mitigations can be used to assist with developing a proportionate and fit-for-purpose RBQM oversight strategy. This resource aligns with the RBQM Oversight Trial Assessment so that any criteria that score medium or high can be translated into concrete actions across the common risk drivers of trial criticality, sponsor experience, service provider history, process novelty, and geographical complexity. By aligning mitigations with these criteria, sponsors can ensure their RBQM oversight remains proportionate, targeted, and evidence-based rather than generic or duplicative. The example mitigations in this resource are intended to prompt critical thinking rather than serve as a prescriptive checklist. These actions may be revisited during the trial as new information emerges or as risks evolve.
Learning Resource D: RBQM Reflective Questions
The RBQM Reflective Questions are intended to support ongoing evaluation of RBQM implementation during trial conduct . They are example questions grouped by category that are designed to assist in a conversation about the RBQM implementation. They can be used to gain an insight into the RBQM process in action and the discussions may lead to the RBQM oversight level being adjusted. These questions help surface evidence about how effectively risks – particularly those affecting participant safety or data reliability – are being managed. Unlike prescriptive checklists, these questions are intended to stimulate critical thinking, encourage dialogue across functions and between sponsor and service provider(s), and provide a practical way to verify that risk management activities are both meaningful and effective. The questions are grouped into nine areas and are provided below. They are intended to guide structured dialogue and support critical thinking, rather than serve as a formal scoring mechanism. Note that many of the questions relate to activities that should have occurred prior to First Participant First Visit.
Disclaimer:
The RBQM Oversight Learning Resources developed by the mindsON RBQM Expert Working Group (EWG) are intended for use by professionals with technical skills and knowledge in the pharmaceutical and biotechnology industries. Neither the EWG nor their respective employers make any warranties or assume any legal liability or responsibility for the accuracy, completeness, or usefulness of the information provided. It is the responsibility of the user to ensure that the information is suitable for their intended use. Neither the EWG nor their respective employers are responsible for any inaccuracies in the Learning Resources or for any advice provided. Additionally, the user is responsible for protecting their data from potential errors, viruses, or bugs, and is prohibited from distributing or selling the Learning Resources without written consent from the EWG. Neither the EWG nor their employers will be held liable for any damages resulting from the use of the Learning Resources. This document is provided 'as is' without warranty of any kind, either expressed or implied, including, but not limited to, the implied warranties of merchantability, fitness for a particular purpose or non-infringement.
This is not a validated Tool. Ensure validation as applicable per your company requirements.
The content can be modified or adopted to specific company needs.

## Resource D
Resource D: RBQM Reflective Questions
| Area | Example Questions
1 | Critical to Quality Factors | Have Critical to Quality Factors (CTQs) been defined? How were they defined? Who was involved in defining them? Are they study specific or only generic? Have they been reviewed? Is there a review planned?
2 | Risk Assessment | Has a risk assessment been conducted? Who was involved? Did it include appropriate cross-functional representation? Is it documented? And approved by the appropriate functions? What key risks were identified? Are there risk owners? How do those key risks relate to critical to quality factors? Are the risks study specific? How have prioritized risks been mitigated? Have those mitigations been implemented? Has a proportionate approach been used? Has the risk assessment been reviewed during the trial? When and why? What changes were made? When is the next review planned?
3 | Quality Tolerance Limits (QTLs) and Acceptable Ranges (ARs) | Have QTLs or ARs been defined for this study? If not, what is the rationale? Do they relate to the risks to the CTQs? How were the thresholds determined? Are there metrics such as QTLs, ARs or KRIs designed to detect an emerging issue early? How are the QTLs/ARs calculated and reviewed? Have there been any deviations from the QTLs/ARs? If so, how were they handled? Will they be reported in the Clinical Study Report? If there are no deviations, is that expected? Or could there be an issue with programming?
4 | Key Risk Indicators (KRIs) | Are KRIs being monitored for the study? If not, what is the rationale? How many KRIs are being monitored for this study? How many of those are common across studies? How many study-specific? How were they selected? Are there study level and site levels KRIs? Are there country, regional and/or CRA level KRIs? How were the thresholds determined? Have they been validated? How are they calculated and reviewed? Who is involved in reviews? Is the output documented? What actions are taken based on the ouput? How is it determined whether any actions are effective? Have the KRIs (the metrics and/or thresholds) been reviewed for effectiveness? Have any changes been made? When is the next review planned?
5 | Centralized Statistical Monitoring (CSM) | Is CSM being used for the study? If not, what is the rationale? What statistical tests are used to assess the accumulating data? How is CSM performed - who by and when? Is the output documented? How is the output reviewed? Who is involved in the reviews? What actions are taken based on the output? How is it determined whether any actions are effective?
6 | Communication | How have key risks and their mitigations been communicated and documented for regulatory inspection? How have Critical to Quality Factors been communicated? Are mitigations documented in study plans? Who have they been communicated to? When was the communication? Has there been any follow-up?
7 | Personnel | How are RBQM responsibilities split between roles? Are people clear on what their responsibilities are as part of RBQM? Has there been any recent change of key personnel involved with RBQM? Is the split between RBQM activities between the service provider and the sponsor clear? How does this align with oversight tier and RACI documentation? Can the study team describe examples of how RBQM activities relate to maintaining participant safety, rights, well-being or to data integrity? Is there evidence of critical thinking and open dialogue across functions implementing RBQM?
8 | Site Monitoring | Is site monitoring frequency and strategy dependent on the perceived level of risk? If not, what is the rationale? If so, how does that work? Is the approach effective? Is the approach being used risk-proportionate and linked back to the risk assessment? Has monitoring verified that any agreed risk mitigations were implemented and are effective? Are KRIs used for this purpose? Are there any issues or risks from site monitoring that have been considered as possible systemic issues for the trial? If so, how were these managed and escalated? Has the approach being used been reviewed during the study? When is the next planned review?
9 | Significant Changes or Concerns | Significant changes might impact many aspects of the RBQM system as well as its oversight. For example: .Has there been a major protocol amendment? .Have there been significant challenges with a critical service provider? .Is there a new service provider for a critical area? .Is there a new geography planned beyond what was originally expected? Are there concerns about the functioning of the RBQM process/system? If so, an increased level of oversight might be needed.